## INSTRUCTIONS
Introduction/Aim | This worksheet is intended to work as tangible guidelines to get insight and specify the different communication challenges between actors when bringing a Marine Biotechnology innovation through the value chain from lab to the market
How is it divided | There is one sheet for each of the 6 different steps in the value chain
Probability | Score the probability for how each challenge is relevant for the work to be done to bring your innovation through the value chain. Give it a score from 1 (low probability) to 5 (high probability)
Impact | What impact will the challenge have on the efficient development of your innovation? Give it a score from 1 (low impact to 5 (high impact)
PI | The PI factor is calculated as Probability x Impact and can range from 1 to 25. Sorting the challenges after the PI factor from high to low give a good indication on how to prioritize your resources.
Responsible | In the "Responsible" column you can assign the task to specific partners in your consortium
Checkbox | When the challenge has been tackled you can check the box
More challenges | This list is not complete - add lines and challenges as you need

## 1. KNOWLEDGE OUTPUT
1. KNOWLEDGE OUTPUT – THE START | Communication challenges | Action idea to minimize risk | Probability | Impact | PI | Responsible | Checkbox
Ojectives: To clearly describe the knowledge obtained, to be communicated to scientific audience, potential stakeholders/industry and public. - Initial, tentative questions: - What is the novelty? - Presumed application area(s)? - Is there a presumed market pull, or is it purely technology push? | Is the description of the academic knowledge output well formulated for external uptake by delopment managers? | Seek external feedback and if needed, improve communication skills |  |  | 0
| Are the messages too complex? | Simplify description and ask people from outside your field to read through your text |  |  | 0
| Business people don’t understand the idea | Train the scientist/supervisor to produce the needed information – orally and in written form |  |  | 0
| Is my information adapted for the different stakeholders? | Have different "pitch" talks for other scientist, tech transfer officers, capital owners, company boards … |  |  | 0
| Is the potental value/application areas of my knowledge output estimated to its full potental? | Seek recognition and refer to similar work and publications to benchmark |  |  | 0
| Do I need external expertise | Be concrete and contact knowledge brokers |  |  | 0
| Is novelty sufficient? Do I have legal freedom to operate? | Do patent searches |  |  | 0
| Is my knowledge output legally secured? | Make a patent/publish strategy and seek advice/help from a TTO, patent lawyer or similar |  |  | 0

## 2. TOWARDS COMMERCILISATION
2. SETTING TIMELINES AND DEFINING FORESEEN STEPS TOWARDS COMMERCIALISATION Ojectives: Setting the team to realise the knowledge output: - Researcherrs - TTO representatives - Regulatory expertise - Marketing expertise (process) - Application area expert - User Consider if leadership may be too academic. | Communication challenges | Action idea to minimize risk | Probability | Impact | PI | Responsible | Checkbox
| Build trust between partners | Make agreements between parties:
|  | - Make confidentiality agreement |  |  | 0
|  | - Initiate agreements for oral communication |  |  | 0
|  | - Make agreements for written communication |  |  | 0
|  | - Make agreements for documentation: - who should be informed about what |  |  | 0
| Understand industry's interest in our knowledge output | Work with industry to make them more receptive to knowledge output from academia |  |  | 0
| Set realistic timelines and budgets | - Do not oversell |  |  | 0
|  | - Keep focus |  |  | 0
| Understand implications of TRL stage | Be aware of how TRL may affect the tasks to be communicated and done |  |  | 0
| Communication with TTO | Ascertain that TTO representative understand the knowledge output |  |  | 0
| Create positive interest from downstream users | Plan from start how to communicate with downstream users |  |  | 0
| Obtain information on how marketing opportunities impact timeline | Consider how marketing opportunities/drivers impact project timeline (may become iterative) |  |  | 0
| Lacking forward thinking | Conditions for next step? |  |  | 0
| Think ahead | What are the conditions for next step? |  |  | 0
| Be certain the team is complete and communicate well | Setting the team to realise the knowledge output
|  | - Researcher(s) |  |  | 0
|  | - TTO representative (process owner (IP, coordinate, analyse) |  |  | 0
|  | - Regulatory expertise |  |  | 0
|  | - Marketing expertise (process) |  |  | 0
|  | - Application area expert? |  |  | 0
|  | - User |  |  | 0
|  | - Consider leadership – too academic? |  |  | 0

## 3. PROOF OF PRINCIPLE
3. PROOF OF PRINCIPLE Objectives: Demonstrate the feasibility of the commercialisation by applying the knowledge output in a production setting | Communication challenges | Action idea to minimize risk | Probability | Impact | PI | Responsible | Checkbox
| Need to validate results | Obtain trust in the team and from external parties about previous results. |  |  | 0
| To explain use of methods and validate | Have the right methods been used to validate research results (e.g. animal/human models)? |  |  | 0
| Meet expectations of downstream users | Identify downstream user needs |  |  | 0
| Keep commercial focus in mind | Investigate commercial potential |  |  | 0
| Follow the right quality standards | Identify potential quality standards to be met, and communicated to the team |  |  | 0
| Potential violation of IP rights | Consider ‘freedom to operate’ and rights of all involved, including third parties (TTO task) |  |  | 0
| Obtain mutual understanding between academy and industry actors about principles and working goals | Bring people from factory to lab and vice-versa and initiate open dialoges in the team |  |  | 0

## 4. PROOF OF CONCEPT
4. PROOF OF CONCEPT Objectives: Demonstrate that the concept of the knowledge output has a practical and commercial potential | Communication challenges | Action idea to minimize risk | Probability | Impact | PI | Responsible | Checkbox
| Define infrastructure needed. Equipment from lab to pilot scale. | Communicate need for infrastructure (types, cost, competences). Specify equipment and facilities needed when going from lab to pilot scale. Talk to plant managers.
| Communicate commercial potential | Define level of concept complexity – if too high, hard to communicate commercial potential
| End user needs | Specify end user needs – cultural conditions? Talk to specialists.
| Highlight commercial potential | Set realistic expectations to commercial potential
| Distinguish between real and perceived risks | Settle risk agreements among all team members

## 5. PRECOMMERCIAL TRIALS
5. PRECOMMERCIAL TRIALS Objectives: Final tests before full scale-up of production, tuning involvement and agreements between production partners | Communication challenges | Action idea to minimize risk | Probability | Impact | PI | Responsible | Checkbox
| Investor involvements | Define realistic time and cost aspects, and present realistic production scenarios for investors |  |  | 0
| Engaging entrepreneurs / engineers | Set proper milestones for entrepreneurs/engineers involved |  |  | 0
| Understand regulatory barriers | Check potential regulatory barriers for your marine products and raw material (may be iterative) |  |  | 0
| Obtaining customers' acceptance | Present prototype samples to customers and get feedback |  |  | 0
| Reach out to ‘new’ users or stakeholders and expand network | Consult TTO, team members and experts with market knowledge |  |  | 0

## 6. COMMERCIAL PR & PROCESSES
6. COMMERCIAL PRODUCTS AND PROCESSES Objectives: Securing success of knowledge output commercialisation | Communication challenges | Action idea to minimize risk | Probability | Impact | PI | Responsible | Checkbox
| Obtain consensus among parties in final stages of the value chain | Communicate with production operators, marketing people and business managers involved in final processing |  |  | 0
| Explain value potentials to new markets | Identify opinion leaders and start communicating. Listen carefully and be flexible. |  |  | 0
| Communication with the general public | Discuss your products/processes at their "level". Consult professional media people. |  |  | 0